## Semester 2
User Story | Start | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Sprint 9 | Sprint 10
1.1.9. As a user, I want to detect and access the ambient light sensor so that I can gather ambient light data | 8 | 0 | 0
1.1.10. As a user, I want to detect and access the GPS so that I can gather latitude and longitude data | 8 | 0 | 0
1.1.11. As a user, I want microphone data to be collected without lag in real time so that all my data can be collected in unison | 13 | 0 | 0
1.2.8. As a user I want to collect illuminance from the ambient light sensor so that I have this data for my experiment | 8 | 0 | 0
1.2.9. As a user I want to collect latitude and longitude from the GPS so that I have this data for my experiment | 8 | 0 | 0
2.2.7. As a user I want to generate and update a graph for ambient light luminosity data in real-time, so that I can view my collected data | 8 | 0 | 0
2.2.8. As a user I want to generate and update a graph for GPS latitude and longitude data in real-time so that I can view my collected data | 8 | 0 | 0
3.1.8. As a user I want to store the collected ambient light luminosity, so that I can use it later | 8 | 0 | 0
3.1.9. As a user I want to store the collected GPS latitude and longitude data, so that I can use it later | 8 | 0 | 0
3.2.4. As a user, I want to delete data that I have exported, so that my device storage doesn't fill up with data once I have finished using it | 21 | 0 | 18
4.1.1. As a developer, I want to obtain ethical clearance so that I can test the application with disabled individuals | 34 | 0 | 4
4.1.2. As a developer, I want to test the application with disabled users so that I can optimize the usability of the application | 34 | 0 | 0
4.1.3. As a product owner, I want an apk, so that I can test the android app myself | 8 | 8 | 0
4.1.4. As a product owner, I want an ipa so that I can test the iOS app myself | 8 | 8 | 0
Actual work remaining | 182 | 166 | 144
Ideal work remaining | 182 | 163.8 | 145.6 | 127.4 | 109.2 | 91 | 72.8 | 54.6 | 36.4 | 18.2 | 0

## Semester 1
User Story | Start | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8
1.1.1. As a user, I want to detect and access the magnometer so that I can gather magnetic field data | 8 | 2 | 0 | 0 | 0 | 0 | 6 | 0 | 0
1.1.2. As a user, I want to detect and access the accelerometer so that I can gather acceleration data | 8 | 2 | 4 | 0 | 0 | 2 | 0 | 0 | 0
1.1.3. As a user, I want to detect and access the gyroscope so that I can gather orientation and angular velocity data | 8 | 2 | 0 | 0 | 0 | 0 | 6 | 0 | 0
1.1.4. As a user, I want to detect and access the microphone so that I can gather audio | 8 | 2 | 4 | 0 | 0 | 2 | 0 | 0 | 0
1.1.5.As a user, I want to detect and access the barometer so that I can gather pressure | 8 | 2 | 0 | 0 | 0 | 0 | 6 | 0 | 0
1.1.6. As a user, I want to detect and access the camera so that I can gather visual data | 8 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 4
1.1.7. As a user, I want a list of available sensors on my device so that I can pick which I want data collected from | 21 | 3 | 3 | 0 | 3 | 9 | 0 | 3 | 0
1.1.8. As a user I want to pick which sensors collect data so that I can tailor the collected data to my experiment | 5 | 0 | 0 | 0 | 2 | 0 | 3 | 0 | 0
1.2.1. As a user I want to collect direction from the magnetometer so that I have this data for my experiment | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
1.2.2. As a user I want to collect acceleration from the accelerometer so that I have this data for my experiment | 8 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0
1.2.3. As a user I want to collect rate of rotation from the gyroscope so that I have this data for my experiment | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
1.2.4. As a user I want to collect pressure from the barometer so that I have this data for my experiment | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 0
1.2.5. As a user I want to collect sound from the microphone so that I have this data for my experiment | 8 | 0 | 4 | 0 | 2 | 2 | 0 | 0 | 0
1.2.6. As a user I want to collect video from the camera so that I have this data for my experiment | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 6
1.2.7. As a user I want to only collect data from selected sensors so that I can tailor the collected data to my experiment | 21 | 0 | 3 | 0 | 3 | 3 | 6 | 3 | 3
2.1.1. As a user I want to label data from a list of labels so that I can keep track of which data relates to different aspects of my experiment | 13 | 0 | 0 | 2 | 3 | 3 | 2 | 0 | 3
2.1.2. As a user I want to label data with a new label so that I can tailor the labels to my experiment | 8 | 0 | 0 | 2 | 2 | 4 | 0 | 0 | 0
2.2.1. As a user I want to generate and update a graph for magnetometer direction in real-time so that I can view my collected data | 13 | 5 | 0 | 2 | 0 | 0 | 6 | 0 | 0
2.2.2. As a user I want to generate and update a graph for acceleration in real-time so that I can view my collected data | 13 | 5 | 0 | 2 | 0 | 6 | 0 | 0 | 0
2.2.3. As a user I want to generate and update a graph for gyroscope rate of rotation data in real-time so that I can view my collected data | 13 | 5 | 0 | 2 | 0 | 0 | 6 | 0 | 0
2.2.4. As a user I want to generate and update a graph for barometer pressure in real-time so that I can view my collected data | 13 | 5 | 0 | 2 | 0 | 0 | 6 | 0 | 0
2.2.5. As a user I want to generate and update a graph for microphone data in real-time so that I can view my collected data | 13 | 5 | 0 | 2 | 0 | 6 | 0 | 0 | 0
2.2.6. As a user I only want to generate graphs for selected sensors so that I don't wast space with empty graphs | 13 | 2 | 0 | 2 | 4 | 4 | 1 | 0 | 0
3.1.1. As a user I want to store the collected magnetometer direction so that I can use it later | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
3.1.2. As a user I want to store the collected acceleration data so that I can use it later | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
3.1.3. As a user I want to store the collected rate of rotation data so that I can use it later | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
3.1.4. As a user I want to store the collected pressure data so that I can use it later | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
3.1.5. As a user I want to store the collected audio data so that I can use it later | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
3.1.6. As a user I want to store the collected videos so that I can use them later | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0
3.1.7. As a user I only want to store data for selected sensors so that I don't have any unnecessary datasets | 13 | 0 | 0 | 0 | 8 | 0 | 0 | 5 | 0
3.2.1. As a user I want to generate a CSV file with data that can be stored in this format so that I can export my data | 13 | 0 | 0 | 5 | 0 | 0 | 0 | 8 | 0
3.2.2. As a user I want to export a CSV file with data that can be stored in this format so that I can have my data on other devices | 13 | 0 | 0 | 5 | 0 | 0 | 0 | 8 | 0
3.2.3. As a user I want to export data that can't be stored in a CSV file so that I can have ALL my data on other devices | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 0
Estimated work remaining | 342 | 299.25 | 256.5 | 213.75 | 171 | 128.25 | 85.5 | 42.75 | 0
Actual work remaining | 342 | 300 | 278 | 252 | 223 | 180 | 108 | 16